## CoverPage
PROJECT PLAN
Project Name |  |  |  | Domain Name System
Project Id |  |  |  | DEC08_TH6_07
Mentor |  |  |  | Rashi Arora
CM |  |  |  | Rashi Arora
Project Start Date |  |  |  | 28 January, 2015
Project End Date |  |  |  | 24 February, 2015
Organizational Structure
Role | Name | Loading (in the given role)
Mentor | Rashi Arora | 30%
Buddy
Developers/Trainees | Deepesh Kumar, Divya Kansal, Shivani badola, Sonia Verma, Sourav Kumar singh | 100%
Rampup/Requirements Phase Lead | Sonia Verma, Sourav Kumar Singh | 100%
Design Phase Lead | Shivani Badola, Sonia Verma | 100%
Coding Phase Lead | Deepesh Kumar, Divya kansal,Sourav Kumar Singh | 100%
UT Phase Lead | Deepesh Kumar, Divya Kansal, Shivani Badola | 100%
Revision History
Rev No. | Date of Issue |  | Author | Approved by | Scope
0.1 | 29 January, 2015 |  |  | Deepesh Kumar, Divya Kansal, Shivani badola, Sonia Verma, Sourav Kumar singh, | Initial Project Planning
0.2 | 31 January, 2015 |  |  | Deepesh Kumar, Divya Kansal, Shivani badola, Sonia Verma, Sourav Kumar singh | Project Requirements Decided
0.3 | 04 Febuary, 2015 |  |  | Deepesh Kumar, Divya Kansal, Shivani badola, Sonia Verma, Sourav Kumar singh | Project Design Decided
0.4 | 11 Febuary, 2015 |  |  | Deepesh Kumar, Divya Kansal, Shivani badola, Sonia Verma, Sourav Kumar singh | Project Coding phase

## Milestones_Q_Targets
Menu
|  | Milestones & Manpower Loading | [9 empty] | Project Planning
Requirements
Project Tracking Information | [11 empty] | Design
Module Name | Phases | Start Date |  |  | End Date |  |  | Schedule Variance (%) | Planned Effort (in per hours) | Actual Effort (in per hours) | Effort Variance (%) | Coding | Coding
|  | Planned | Forecasted | Actual | Planned | Forecasted | Actual |  |  |  |  | Unit Testing | Unit Testing
| Project Planning | 2015-01-28 | 2015-01-29 | 2015-01-29 | 2015-01-28 | 2015-01-30 | 2015-01-30 | 200% | 1 | 2 | 100% | SSI Testing | SSI Testing
| Requirements | 2015-01-31 | 2015-02-01 | 2015-02-01 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 200% | 2 | 2 | 0% | SI Testing | SI Testing
| Design | 2015-02-04 | 2015-02-09 | 2015-02-09 | 2015-02-05 | 2015-02-10 | 2015-02-10 | 125% | 2 | 2 | 0% | Release Testing | Release Testing
| Coding | 2015-02-11 | 2015-02-12 | 2015-02-12 | 2015-02-17 | 2015-02-19 | 2015-02-20 | 85.61% | 4 | 7 | 75% | Acceptance Testing | Acceptance Testing
| Unit Testing | [10 empty] | PQT | PQT
| User Documentation | [10 empty] | Misc. | Misc.
Overall |  | 2015-01-28 | 2015-01-29 | 2015-01-29 | 2015-02-17 | 2015-02-19 | 2015-02-20 | 14.29% | 9 | 13 | 44.44%
Manpower Loading
| Phase / Milestone | <week1> | <week2> | <week3> | <week4> | <week5> | <week6> | <week7> | <week8>
| Peak Team Size | <week1>: 5; <week2>: 5; <week3>: 5
| Planed Effort (Person hrs) | <week1>: 36; <week2>: 36; <week3>: 31
| Actual Effort (Person days) | <week1>: 40; <week2>: 40; <week3>: 34.5
| Variance (%) | <week1>: 11.11%; <week2>: 11.11%; <week3>: 11%
Formulas:
Start Date = MIN(C7:[Start Date, row above])
Forecasted = MIN(D7:[Forecasted, row above])
Forecasted = MAX(G7:[Forecasted, row above])
Actual = MIN(E7:[Actual, row above])
Actual = MAX(H7:[Actual, row above])
End Date = MAX(F7:[End Date, row above])
Note on D6: Shiv Kumar: After a few days into a phase, one can predict the forecasted date of completion - helps in better planning

## Inspection Details
Menu
Artifact Inspection and Reviews Details
Quality Deliverables
| Deliverables | Draft Completion Date | Review Completion Date | Lead | Authors | Reviewers | Remarks |  | Quality Deliverables
| Project Plan 0.1 | 2015-01-28 | 2015-01-29 | Team | Sourav Kumar Singh | Deepesh Kumar, Divya Kansal, Shivani badola, Sonia Verma |  |  | NA
| SRS 0.1 | 2015-01-31 | 2015-02-03 | Team | Shivani Badola | Deepesh Kumar, Divya Kansal, Sonia Verma, Sourav Kumar singh |  |  | NA
| design | 2015-02-09 | 2015-02-10 | Team | Sonia Verma | Deepesh Kumar, Divya Kansal, Shivani Badola, Sourav Kumar singh |  |  | Design Review Checklist, Inspection Logs
| code | 2015-02-16 | 2015-02-17 | Team | Deepesh Kumar | Divya Kansal, Shivani Badola, Sonia Verma, Sourav Kumar singh |  |  | Code Review Checklist, Inspection Logs
[7 empty] | NA |  | Inspection Logs
| S.No. | Artifact Name | Artifact Type | No.of Reviewers | Defects |  | Size |  | Total Effort | Overall size | Defect Density
[5 empty] | Defects | Enhancement | Latest Size | % Modified
| 4 | SI Test Plan | SIT | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Possible Deliverables
|  | Project Plan | PP
|  | S/w Requirement Spec. | Req.
|  | Design | HLD
|  | Code | Code
|  | PICS | Req.
|  | API | LLD
|  | Unit Test Plan | UT
|  | SSI Test Plan | SSIT
|  | SI Test Plan | SIT
|  | RT Test Plan | RT
|  | PQT Test Plan | PQT / AT
|  | Others | Others
Note on B4: Shiv Kumar: This table can be updated in 0.2 of PP
Note on J4: Shiv Kumar: This table can be updated in 0.2 of PP
Note on J15: HSS: Pre Meeting Effort + Meeting Effort in Person Days.
Note on F16: All accepted comments will come under Important whether it is Critical, Major, Minor
Note on G16: Enhancements + Cosmetic Defects
Note on I16: Here % Modified : (# of New Pages/KSLOC added + #of Pages/KSLOC Modified)/(Latest size of Document/Code) E.g. Re-used size of document :60 Pages New pages added in document :10 Pages # of Pages Modified (Re-used pages) :5 Pages Latest size of document:60+10+5=75 % Modified: (10+5)/75=> 20%

## Testing Details
Menu
Testing Defect Details
| Sl.No | Phase | Baseline Code size (ksloc) |  |  |  |  | Severity-wise Distribution |  |  |  |  | Defect Category | [9 empty] | Code Size | Defect Density
|  |  | New | Modified | CASE Tool Generated | Reused | Total | Critical | Major | Minor | Oths / Enh. | Total | Assignment / Initialization | Checking | Algorithm / Method | Function/ Class / Object | Timing/ Serialization / Synchronization | Interface/ O-O Messages | Build/ Package / Environment | Memory Leaks | Documentation | Standards
| 1 |  |  |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
3
4
5
6
7
8
9
10
11
12
13
14
15
| Overall |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on I4: Distribution for UT phase is optional, but total need to be mentioned
Note on N4: 1. For Details/ Definition/ Examples of the defined categories refer to SEPG Guidelines for Defect Prevention 2. Distribution for UT phase is optional
Note on X4: HSS: New + Modified + Case tool Generated
Note on E5: HSS: Irrespective of # of Lines of Code modified, added or deleated, overall size of the file will be considered.
Note on L5: Others Or Enhancement

## Revision_History (hidden)
Revision History
Rev. | Date of issue | Author | Approver | Description of Change
1.4 |  |  | R. Sathya | Initial Version
1.5 |  | Gunjan | R. Sathya | Added Platform, Language and Tools section in the "kick-off" sheet.
1.6 | 2005-07-04 | Shubha | R. Sathya | Incorporated Customer Suppplied Documents and Data in Data Management Plan,Migration Plan and Disaster Recovery Plan in Deliverables sheet
1.7 | 2005-07-28 | Mohit Dhawan | R Sathya | Cover page sheet : divided the roles and responsibilities in the table into 2 columns. Milestones_Q_Targets sheet : added TL 9000 Quality Metrics table Plans_Other Details : transferred Migration plan and Disaster recovery plan from deliverables sheet, Added : IPR/License issues details (if any), Defect Management Plan, Defect Prevention Plan, Risk Management Plan, Release Management Plan, Acceptance Plan and Technical process details. Path to Escalation plan, staffing sheet, training plan, travel plan and oragnization chart, Issue Tracking sheet